## Risk Register
SAPIA SECURITY RISK REGISTER 2019
Risk Identification | [6 empty] | Risk Priority |  |  |  | Mitigation Plan |  |  | Resolution
Risk Number | Risk Category/ Title | Risk Description | Potential Impact | Potential Impact | Identified By | Date Of Identification | Level Of Impact (1- Severe,2=Major,3=Moderate;4=Minor-I5=Marginal) | Probability (1- Almost certain,2=Likely,3=Possible,4=Unlikely,I5=Rare | Risk Value | Risk Value (Rating) | Mitigation Stategy | Assigned To | Deadline | Closed Date
1 | Retail Security | Retail Robberies | 1 | Severe | SAPIA | 2019-03-18 | 1 | 1 | 1 | High Priority |  | Business to manage
2 | Retail Security | ATM Bombings | 2 | Major | SAPIA | 2019-03-18 | 2 | 1 | 2 | High Priority | arrange a meeting with banking sector and police task force | SAPIA and SABRIC
4 | Distribution Risk | Hijacking | 2 | Major | SAPIA | 2019-03-18 | 2 | 3 | 6 | High Priority |  | Business to manage
5 | Value Chain | Civil Unrest | 2 | Major | SAPIA | 2019-03-18 | 2 | 1 | 2 | High Priority | Should be managed with the broader business respects (BUSA) | SAPIA
8 | Depot Security Risk | Depot Security in rural areas | 2 | Major | SAPIA | 2019-03-18 | 2 | 3 | 6 | High Priority |  | SAPIA - during strike
10 | Retail Security | Cash In Transit | 1 | Severe | SAPIA | 2019-03-18 | 1 | 2 | 2 | High Priority | arrange a meeting with banking sector and police task force | SAPIA and SABRIC
13 | Pipeline risk | Sabotage of Pipelines | 2 | Major | SAPIA | 2019-03-19 | 2 | 3 | 6 | High Priority | need to be addressed at the multi stakeholder forum that deal with illegal mining | SAPIA
16 | Pipeline risk | Theft of Pipelines | 2 | Major | SAPIA | 2019-03-18 | 2 | 5 | 10 | Low Priority
19 | Border Security | Lack of security at border posts | 3 | Moderate | SAPIA | 2019-03-18 | 3 | 2 | 6 | High Priority |  | SAPIA/ CBRTA/RFA
22 | Retail Security | Cash on site | 3 | Moderate | SAPIA | 2019-03-19 | 3 | 2 | 6 | High Priority | arrange a meeting with banking sector and police task force | SAPIA and SABRIC
23 | Product Theft | Rail tank cars | 2 | Major | SAPIA | 2019-03-18 | 2 | 2 | 4 | High Priority |  | SAPIA and TFR
24 | Retail Security | CMS Bombing | 2 | Major | SAPIA | 2019-03-18 | 2 | 1 | 2 | High Priority | arrange a meeting with banking sector and police task force | SAPIA and SABRIC
25 | Value Chain | Illegal Mining | 1 | Severe | SAPIA | 2019-03-18 | 1 | 2 | 2 | High Priority | Should be managed with the broader business respects (BUSA) | SAPIA

## Risk Matrix
P1 - Amost Certain |  |  |  | 5 | 1
|  |  |  | 6 | 17
24
P2 - Likely |  | 12 | 8 | 11 | 2
|  |  | 19 | 20 | 10
|  |  | 22 | 23 | 25
P3 - Possible |  |  | 7 | 3
4
13
14
P4 - Unlikely |  | 18 |  |  | 9
P5 - Rare |  |  |  | 15
16
21
| I5 -Marginal | I4-Minor | I3-Moderate | I2-Major | I1-Severe
Probability
Impact
SAPIA - Risk Matrix